## ACTION PLAN
CONCEPT STAGE ACTION PLAN
STEP # | ACTION REQUIRED | ü | WHO IS RESPONSIBLE | START DATE | END DATE | COMMENTS
C-1 | IDENTIFY OPPORTUNITY:
PROPERTY OPPORTUNITY
NEED / USE / IDEA OPPORTUNITY
C-2 | ASSEMBLE CO-DEVELOPMENT TEAM
C-3 | DEFINE ROLE OF CO-DEVELOPERS:
OBJECTIVES
CONTRIBUTIONS
C-4 | CONSIDER APPROPRIATENESS OF CID
C-5 | FORMULATE SKELETAL PLAN
C-6 | IDENTIFY INFORMATION SOURCES AND ASSEMBLE AVAILABLE STUDIES
C-7 | IDENTIFY SOURCES OF HELP
C-8 | REVIEW AVAILABLE INFORMATION
C-9 | IDENTIFY SEED MONEY: SOURCE/USE
C-10 | EVALUATE INVESTMENT CLIMATE
C-11 | COMPARE OBJECTIVES, CONTRIBUTIONS AND CLIMATE
C-12
C-13
C-14 | DECISION POINT - OPTIONS:
ABANDON PROJECT
RECONSIDER THIS STAGE
REVISE OBJECTIVES
REVISE CONTRIBUTIONS
PROCEED TO NEXT STAGE
© 2006 National Trust Main Street Center

## C-2
FORM C-2: CO-DEVELOPMENT TEAM (NO MORE THAN SEVEN MEMBERS)
TEAM MEMBERS | ü | WHO CONTACTS | DATE NEEDED | NAME | PHONE # | E-MAIL
POSSIBLE MEMBERS
DEVELOPER
LENDER
INVESTOR
BUILDING OWNER
USER(S)
NONPROFIT ENTITY
PUBLIC ENTITY
OTHER POSSIBLE MEMBERS FROM "TECHNICAL ASSISTANCE TEAM" LIST
ATTORNEY
REAL ESTATE BROKER
ACCOUNTANT
ARCHITECT
CONSULTANT
GENERAL CONTRACTOR
PROPERTY MANAGER
© 2006 National Trust Main Street Center

## C-3A
FORM C-3A: OBJECTIVES OF CO-DEVELOPMENT TEAM MEMBERS
MEMBER | OBJECTIVES | PRIMARILY
|  | ECON | SOC | PHY | POL
NOTES:
© 2006 National Trust Main Street Center

## C-3B
FORM C-3B: CONTRIBUTIONS OF CO-DEVELOPMENT TEAM
MEMBER | CONTRIBUTION | ü | AMOUNT OR NATURE
| MONEY |  | $
LAND AND/OR BUILDING
TIME AND/OR EXPERTISE
OCCUPANCY
PUBLIC OR POLITICAL SUPPORT
NONMONETARY SUPPORT
| SEED MONEY |  | $
FUND RAISING
OTHER
| MONEY |  | $
LAND AND/OR BUILDING
TIME AND/OR EXPERTISE
OCCUPANCY
PUBLIC OR POLITICAL SUPPORT
NONMONETARY SUPPORT
| SEED MONEY |  | $
FUND RAISING
OTHER
| MONEY |  | $
LAND AND/OR BUILDING
TIME AND/OR EXPERTISE
OCCUPANCY
PUBLIC OR POLITICAL SUPPORT
NONMONETARY SUPPORT
| SEED MONEY |  | $
FUND RAISING
OTHER
| MONEY |  | $
LAND AND/OR BUILDING
TIME AND/OR EXPERTISE
OCCUPANCY
PUBLIC OR POLITICAL SUPPORT
NONMONETARY SUPPORT
| SEED MONEY |  | $
FUND RAISING
OTHER
© 2006 National Trust Main Street Center
FORM C-3B: CONTRIBUTIONS OF CO-DEVELOPMENT TEAM CONTINUED
MEMBER | CONTRIBUTION | ü | AMOUNT OR NATURE
| MONEY |  | $
LAND AND/OR BUILDING
TIME AND/OR EXPERTISE
OCCUPANCY
PUBLIC OR POLITICAL SUPPORT
NONMONETARY SUPPORT
| SEED MONEY |  | $
FUND RAISING
OTHER
| MONEY |  | $
LAND AND/OR BUILDING
TIME AND/OR EXPERTISE
OCCUPANCY
PUBLIC OR POLITICAL SUPPORT
NONMONETARY SUPPORT
| SEED MONEY |  | $
FUND RAISING
OTHER
| MONEY |  | $
LAND AND/OR BUILDING
TIME AND/OR EXPERTISE
OCCUPANCY
PUBLIC OR POLITICAL SUPPORT
NONMONETARY SUPPORT
| SEED MONEY |  | $
FUND RAISING
OTHER
| MONEY |  | $
LAND AND/OR BUILDING
TIME AND/OR EXPERTISE
OCCUPANCY
PUBLIC OR POLITICAL SUPPORT
NONMONETARY SUPPORT
| SEED MONEY |  | $
FUND RAISING
OTHER
© 2006 National Trust Main Street Center
Note on B2: Co-development team: The group of individuals (usually volunteers) who initiate, define, guide, and facilitate the Community Initiated Development from conception through completion.
Note on B42: Co-development team: The group of individuals (usually volunteers) who initiate, define, guide and facilitate the Community Initiated Development from conception through completion.

## C-4
FORM C-4: CONSIDER APPROPRIATENESS OF COMMUNITY INITIATED DEVELOPMENT
ü IF APPLICABLE | REASONS TO PURSUE COMMUNITY INITIATED DEVELOPMENT
1. PRIVATE SECTOR CAN'T ACT -- (If checked, complete section below)
2. PRIVATE SECTOR WON'T ACT -- (If checked, complete section below)
3. NEED TO INFLUENCE NATURE, SCALE, TIMING OF DEVELOPMENT
4. PUBLIC PURPOSE / PUBLIC BENEFIT
5. DEVELOPMENT AS CATALYST
6. AN ORGANIZATION IS NEEDED AS CONDUIT FOR FUNDS
7. MAJOR INFRASTRUCTURE IS REQUIRED
8. EMINENT DOMAIN IS NECESSARY
ü IF APPLICABLE | WHY PRIVATE SECTOR CAN'T / WON'T ACT
A. NO FINANCING IS AVAILABLE
B. NO ACCEPTABLE FINANCING IS AVAILABLE
C. THERE IS A HIGH DEGREE OF ACTUAL RISK
D. THERE IS A HIGH DEGREE OF PERCEIVED RISK
E. THE PROPERTY CANNOT BE ACQUIRED
F. OTHER INVESTMENTS MORE ATTRACTIVE
G. PROJECT SCALE TOO BIG OR TOO SMALL
H. RISK / REWARD RELATIONSHIP OUT OF BALANCE
I. PROJECT INCLUDES SIGNIFICANT PUBLIC BENEFITS
J. NOT REVENUE PRODUCING
K. NOT NET REVENUE PRODUCING
L. GENERAL ECONOMIC CONDITIONS
M. HIGH TRANSACTION COSTS
N. COST IS GREATER THAN VALUE
© 2006 National Trust Main Street Center
Note on C3: Community Initiated Development: A process of nontraditional real estate development distinguished by four characteristics: (1) the idea originates from the public or nonprofit sectors; (2) a co-development team is active in the development process; (3) substantial commitment of public or nonprofit resources; (4) the project includes substantial public benefits.
Note on C11: Eminent domain: The right of the government to take private property for public use through the act of condemnation upon the payment of just compensation. This is an exercise of the police power.

## C-5
FORM C-5: PRELIMINARY TIME BUDGETS - ESTIMATED COMPLETION DATE:
DEVELOPMENT STAGE | 1ST DRAFT | [5 empty] | REVISION #1 | [5 empty] | REVISION #2 | [5 empty] | REVISION #3
DATE OF ESTIMATE
CONCEPT
ANALYSIS
PREPARATION
IMPLEMENTATION
OPERATION*
PRELIMINARY MONEY BUDGETS - ESTIMATE OF MONEY REQUIRED $
DATE OF ESTIMATE:
CONCEPT | $ |  | #DIV/0! | % | #DIV/0! | % | $ |  | #DIV/0! | % | #DIV/0! | % | $ |  | #DIV/0! | % | #DIV/0! | % | $ |  | #VALUE! | % | #VALUE! | %
ANALYSIS | $ |  | #DIV/0! | % | #DIV/0! | % | $ |  | #DIV/0! | % | #DIV/0! | % | $ |  | #VALUE! | % | #VALUE! | % | $ |  | #VALUE! | % | #VALUE! | %
PREPARATION | $ |  | #DIV/0! | % | #DIV/0! | % | $ |  | #DIV/0! | % | #DIV/0! | % | $ |  | #VALUE! | % | #VALUE! | % | $ |  | #VALUE! | % | #VALUE! | %
IMPLEMENTATION | $ |  | #DIV/0! | % | #DIV/0! | % | $ |  | #DIV/0! | % | #DIV/0! | % | $ |  | #VALUE! | % | #VALUE! | % | $ |  | #VALUE! | % | #VALUE! | %
OPERATION* | $ |  | #DIV/0! | % | #DIV/0! | % | $ |  | #DIV/0! | % | #DIV/0! | % | $ |  | #VALUE! | % | #VALUE! | % | $ |  | #VALUE! | % | #VALUE! | %
SUBTOTAL | $ | 0 | #DIV/0! | % | #DIV/0! | % | $ | 0 | #DIV/0! | % | #DIV/0! | % | $ | 0 | #DIV/0! | % | #DIV/0! | % | $ | 0 | #VALUE! | % | #VALUE! | %
ACQUISITION | $ |  | #DIV/0! | % |  |  | $ |  | #DIV/0! | % |  |  | $ |  | #VALUE! | % |  |  | $ |  | #VALUE! | %
TOTAL | $ | 0 | #DIV/0! | % |  |  | $ | 0 | #DIV/0! | % |  |  | $ | 0 | #DIV/0! | % |  |  | $ | #VALUE! | #VALUE! | %
*THROUGH RENT-UP OF PROPERTY ONLY
© 2006 National Trust Main Street Center
Note on C11: Add values into fields and sheet will automatically calculate for you.
Note on D12: Add values into the fields and they will automatically calculate for you.
Note on I11: Add values into fields and sheet will automatically calculate for you.
Note on O11: Add values into fields and sheet will automatically calculate for you.
Note on U11: Add values into fields and sheet will automatically calculate for you.

## C-6A
FORM C-6A: IDENTIFY INFORMATION SOURCES
INFORMATION SOURCE | ü | WHAT IS AVAILABLE | WHO IS CHECKING | DATE DUE
CITY HALL / COUNTY COURT HOUSE
PLANNING OFFICE
ZONING OFFICE
COMMUNITY DEVELOPMENT
ECONOMIC DEVELOPMENT
BUILDING INSPECTION
PUBLIC WORKS
ASSESSOR
MAYOR / CITY MANAGER
REGISTER OF DEEDS
REGIONAL PLANNING OFFICE
REAL ESTATE BROKERS
PROPERTY MANAGEMENT FIRMS
LOCAL DEVELOPMENT CORPORATION
CHAMBER OF COMMERCE
LOCAL PROPERTY OWNERS
NEWSPAPER
LOCAL APPRAISERS
ACCOUNTANTS
ATTORNEYS
LOCAL MERCHANTS
INVESTMENT CLUBS
RADIO / TELEVISION STATIONS
BANKERS
LOCAL LIBRARY
LOCAL COLLEGE
STATE UNIVERSITY
INDUSTRIAL DEVELOPMENT GROUP
PRESERVATION ORGANIZATION
LOCAL ADVOCACY GROUP
© 2006 National Trust Main Street Center

## C-6 B
FORM C-6B
SUMMARY OF:
DATE OF STUDY:
AUTHOR OF STUDY:
© 2006 National Trust Main Street Center

## C-8 A
FORM C-8A: WHAT ARE THE BARRIERS TO CONTINUING?
PHYSICAL CONSTRAINTS:
POLITICAL CONSTRAINTS:
LEGAL LIMITATIONS:
MARKET DEMAND OR ACCEPTANCE:
© 2006 National Trust Main Street Center

## C-8 B
FORM C-8B: OPPORTUNITIES AND BENEFICIARIES
OPPORTUNITIES: | BENEFICIARIES:
ECONOMIC
1
2
3
4
PHYSICAL
1
2
3
4
SOCIAL
1
2
3
4
POLITICAL
1
2
3
4
NOTES:
© 2006 National Trust Main Street Center

## C-8 C
FORM C-8 C: PROFILE OF PROJECT (PROPERTY OR USE/IDEA/NEED)
LIMIT PROFILE TO ONE PAGE!
© 2006 National Trust Main Street Center

## C-9
FORM C-9: SEED MONEY
SEED MONEY CATEGORY | SEED MONEY USE | ü | $ REQUIRED |  | SOURCE OF FUNDS
DESIGN / CONSTRUCTION | ARCHITECTURE |  | $
| ENGINEERING |  | $
| PLANNING |  | $
| COST ESTIMATING |  | $
$
$
STUDIES | APPRAISAL |  | $
| FEASIBILITY STUDY |  | $
$
$
PROFESSIONAL SERVICES | ATTORNEY |  | $
| ACCOUNTANT |  | $
$
$
ADMINISTRATIVE COSTS |  |  | $
$
$
PROPERTY COSTS | OPTION MONEY |  | $
| PERMITS |  | $
$
$
OTHER |  |  | $
$
$
TOTAL |  |  | $ | 0
© 2006 National Trust Main Street Center

## C-10
FORM C-10: INVESTMENT CLIMATE MATRIX
FORCE OF VALUE | VIEWPOINT | EXCELLENT | GOOD | FAIR | POOR
ECONOMIC | DEBT-ATTITUDE
EQUITY-ATTITUDE
HEALTH OF COMMUNITY
HEALTH OF TARGET AREA
SOCIAL | COMMUNITY ATTITUDE
NEIGHBORHOOD ATTITUDE
POLITICAL | CITY HALL
ADVOCACY GROUPS
PHYSICAL | BUILDINGS
INFRASTRUCTURE
PUBLIC FACILITIES
NOTES:
© 2006 National Trust Main Street Center

## C-11 A
FORM C-11A: COMPARISON OF OBJECTIVES AND CONTRIBUTIONS
CO-DEVELOPMENT TEAM MEMBER | OBJECTIVES | CONTRIBUTIONS
$
$
$
$
$
$
$
$
CONSIDER: RISK, TIMING, AMOUNT OF CONTRIBUTION
© 2006 National Trust Main Street Center

## C-11 B
FORM C-11B: COMPARISON OF CO-DEVELOPMENT TEAM OBJECTIVES AND INVESTMENT CLIMATE
ECONOMIC OBJECTIVES | 1 | ECONOMIC CLIMATE
2
3
4
5
6
7
POLITICAL OBJECTIVES | 1 | POLITICAL CLIMATE
2
3
4
5
6
7
SOCIAL OBJECTIVES | 1 | SOCIAL CLIMATE
2
3
4
5
6
7
PHYSICAL OBJECTIVES | 1 | PHYSICAL CLIMATE
2
3
4
5
6
7
© 2006 National Trust Main Street Center

## C-14
FORM C-14: DECISION POINT - OPTIONS
DECISION | ü | ACTION REQUIRED
ABANDON PROJECT |  | NO FURTHER ACTION REQUIRED
RECONSIDER THIS STAGE |  | RETURN TO STEP:
REVISE OBJECTIVES |  | RETURN TO STEP C-7 A
REVISE CONTRIBUTIONS |  | RETURN TO STEP C-7 B
PROCEED TO NEXT STAGE |  | GO TO STEP A-1
NEED TO REVISE PRELIMINARY TIME BUDGET? |  | RETURN TO STEP C-5
NEED TO REVISE PRELIMINARY MONEY BUDGET? |  | RETURN TO STEP C-5
NEED TO ADD TO OR CHANGE CO-DEVELOPMENT TEAM? |  | RETURN TO STEP C-2
NOTES:
© 2006 National Trust Main Street Center